COMPANION MATERIAL

# 90-Day SMART OKR Implementation Guide

A controlled pilot roadmap from readiness diagnosis to a responsible scaling decision

SMART OKRs: From Strategic Formulation to Results-Driven Execution

Cristiano de Moraes

How to use This roadmap assumes a controlled pilot. Shorten or extend phases according to context, but preserve the learning logic: diagnose before scaling, define decision rights, measure adoption outcomes, and stop rituals that do not improve decisions.

# Before Day 1 — Decide Whether to Start

Objective: Make the management problem, scope, sponsorship, and success criteria explicit.

## Essential actions

Name the management problem OKRs are expected to improve.

Select a bounded pilot with relevant uncertainty and manageable dependencies.

Define the sponsor and accountable pilot owner.

Set adoption outcomes and guardrails.

State what the pilot will not attempt to solve.

## Verifiable outputs

☐ Pilot charter

☐ Scope and exclusions

☐ Success criteria

☐ Sponsor commitment

# Days 1–15 — Diagnose Readiness and Contradictions

Objective: Understand the real system before introducing the framework.

## Essential actions

Assess strategic clarity, capacity, authority, data, governance, incentives, and psychological safety.

Map current goals, projects, products, mandatory work, and hidden priorities.

Identify where leaders ask for autonomy but retain approvals.

Document conflicting incentives and metric definitions.

Decide what must be fixed before formulation.

## Verifiable outputs

☐ Readiness assessment

☐ Portfolio map

☐ Contradiction map

☐ Preconditions and risks

# Days 1–15 — Prepare Leadership Behavior

Objective: Align leadership behavior with the management system the pilot requires.

## Essential actions

Practice explicit trade-offs and removal of priorities.

Agree how leaders will respond to risk, missed targets, and bad news.

Define decisions delegated to teams.

Separate OKRs from automatic individual performance ratings.

Commit to protecting capacity.

## Verifiable outputs

☐ Leadership commitments

☐ Delegation boundaries

☐ Response-to-risk protocol

☐ Protected capacity

# Days 16–30 — Formulate the Pilot OKRs

Objective: Create a small set of coherent OKRs connected to a real strategic challenge.

## Essential actions

Use the formulation canvas to define the challenge and strategic choice.

Write one to three Objectives for the pilot.

Develop causal hypotheses before selecting metrics.

Convert initiatives into outcome hypotheses.

Run a red-team review.

## Verifiable outputs

☐ 1–3 pilot OKRs

☐ Causal chains

☐ Assumptions register

☐ Red-team findings

# Days 16–30 — Build Measurement Contracts

Objective: Make KRs verifiable and actionable.

## Essential actions

Define formulas, populations, exclusions, baselines, targets, owners, and update frequency.

Identify data quality issues and delays.

Add leading, lagging, and guardrail indicators.

Define thresholds for action.

Remove metrics that cannot support a decision.

## Verifiable outputs

☐ Measurement contracts

☐ Baseline report

☐ Data-quality risks

☐ Action thresholds

# Days 16–30 — Establish Minimum Governance

Objective: Define who decides, how dependencies are resolved, and how changes are controlled.

## Essential actions

Create the governance charter.

Assign Objective, KR, and data owners.

Define strategic, tactical, and operational forums.

Set escalation criteria.

Define rules for changing KRs, targets, baselines, or scope.

## Verifiable outputs

☐ Governance charter

☐ Decision rights matrix

☐ Forum calendar

☐ Change rules

# Days 31–60 — Run Evidence-Based Check-ins

Objective: Use the cycle to make decisions, not merely update percentages.

## Essential actions

Update verified KR values and confidence.

Separate facts, interpretations, and decisions.

Log learning, risks, and dependencies.

Decide whether to continue, adapt, pause, stop, escalate, or invest.

Remove fields and rituals that do not influence decisions.

## Verifiable outputs

☐ Check-in records

☐ Decision log

☐ Dependency actions

☐ Learning register

# Days 31–60 — Review the Portfolio

Objective: Treat initiatives as bets and reallocate capacity based on evidence.

## Essential actions

Link every active initiative to an intended KR and mechanism.

Assess evidence strength, time to learn, cost, reversibility, and risk.

Pause or stop initiatives without a current evidence milestone.

Identify KRs with no funded hypothesis.

Protect mandatory work through explicit guardrails.

## Verifiable outputs

☐ Portfolio decisions

☐ Capacity reallocation

☐ Stopped or adapted bets

☐ Next evidence milestones

# Days 61–75 — Conduct the Mid-Cycle Review

Objective: Reassess trajectory, context, and validity of the hypotheses.

## Essential actions

Review changes in context and data quality.

Compare trajectory with horizon and metric lag.

Change targets only with explicit rules and traceability.

Redesign KRs when the metric no longer represents the phenomenon.

Simplify governance based on observed value.

## Verifiable outputs

☐ Hypothesis review

☐ Capacity decisions

☐ Justified changes

☐ Simplification list

# Days 76–90 — Close, Learn, and Decide on Scale

Objective: Convert pilot experience into a management-system decision.

## Essential actions

Evaluate results, causal validity, execution, measurement, and context separately.

Identify ignored signals, late decisions, and adverse effects.

Measure adoption outcomes: fewer priorities, decisions made, dependency resolution, and initiatives stopped.

Decide whether to repeat, adapt, expand, or end the approach.

Define prerequisites for the next wave.

## Verifiable outputs

☐ Learning report

☐ Adoption outcome report

☐ Scaling decision

☐ Next-wave prerequisites

# Adoption Outcome Scorecard

| Adoption outcome | Possible evidence | Guardrail | Decision supported |
| --- | --- | --- | --- |
| Real focus | Number of simultaneous priorities and initiatives | Mandatory commitments left unprotected | Reduce scope or protect capacity |
| Evidence-based decisions | Share of check-ins with a recorded decision | Update bureaucracy | Keep or simplify cadence |
| Portfolio adaptation | Bets adapted, paused, or stopped | Instability without criteria | Review decision rights and evidence milestones |
| Cross-functional collaboration | Time to resolve material dependencies | Excessive escalation | Delegate or create explicit agreements |
| Measurement quality | KRs with contracts, baselines, and data owners | Collection cost | Invest, replace, or remove the metric |
| Safety and learning | Risks disclosed before results turn red | Normalization of low performance | Change leadership response |